## WBS
Work Breakdown Structure | [9 empty] | Name of Project
| Project Start | 2017-06-23
PERT Estimate
Level | WBS | Task Description | Assigned To | Start | End | Low | Mid | High | Avg | Notes
1 | 1 | Analytic & Documents |  |  |  | 1 | 2 | 4 | 2.1667
2 | 1.1 | Task Level 2 Description
2 | 1.2 | Task Level 2 Description
3 | 1.2.1 | Task Level 3 Description
3 | 1.2.2 | Task Level 3 Description
4 | 1.2.2.1 | Task Level 4 Description
4 | 1.2.2.2 | Task Level 4 Description
4 | 1.2.2.3 | Task Level 4 Description
2 | 1.3 | Task Level 2 Description
1 | 2 | Development
2 | 2.1 | Task Level 2 Description
3 | 2.1.1 | Task Level 3 Description
3 | 2.1.2 | Task Level 3 Description
1 | 3 | Deployment
2 | 3.1 | Task Level 2 Description
3 | 3.1.1 | Task Level 3 Description
4 | 3.1.1.1 | Task Level 4 Description
2 | 3.2 | Task Level 2 Description
1 | 4 | Testing
2 | 4.1 | Task Level 2 Description
1 | 5 | Management
Note on G6: Linh Dang: Three Point Technique This method utilizes a formula that comes from probability theory. Three estimates are made for the duration of a task: O: Optimistic - the shortest duration one has had or might expect to experience given that everything happens as was expected. P: Pessimistic - the duration that would be experienced if everything that could go wrong did go wrong and yet the task was completed. M: Most Likely - the duration that would most likely occur if the task were to repeated over and over again. The formula is then expressed: E = (O + 4M + P)/6 An individual or a group may perform this method. When done by a group the averages of the three estimates are used for O, P, and M.

## References
PERT | https://support.office.com/en-us/article/Use-a-PERT-analysis-to-estimate-task-durations-864b5389-6ae2-40c6-aacc-0a6c6238e2eb